## Central_Tracker
SR.NO | Activity | Technology | Activity Driven By | Start Date | Status | Activity Description | Completion Date
1 | Selecting AUT | Project Management | ALL | 2022-11-07 | Completed | Going through different sources to find AUT | 2022-12-07
2 | Problem Statement | Project Management |  | 2022-12-07 | Completed | Finalizing Problem Statement | 13/07/2022
3 | Git Implemetation | GIT | ALL | 2022-01-10 | Completed | Creating repositories and setting it up on PSL Machines | 2022-02-10
4 | Manual Test Case Writing | Manual Testing | ALL | 2022-12-07 | Completed | Writing Manual Test cases for all the pages | 20/07/2022
5 | Meeting for manual testcases query | Project Management |  | 13/07/2022 | Completed | Reviewing the Manual Test Cases | 13/07/2022
6 | Status Accounting Meeting | Project Management |  | 28/08/2022 | Completed | Status Accounting meeting with Anuprita & Varsha | 29/08/2022
7 | Meeting for manual testcases finalization | Project Management |  | 30/07/2022 | Completed | Finalizing merged Manual Test Cases | 30/07/2022
8 | Automating Test Cases | Selenium |  | 25/08/2022 | Completed | Automating Manual Test Cases using Selenium with Java | 2022-05-09
9 | Creating Daily Activity Tracker | Project Management |  | 26/08/2022 | Completed | Creating Activity Tracker | 27/08/2022
10 | Scrum Meetings | Project Management |  | 27/08/2022 | Completed | Daily Scrum Meetings | 28/08/2022
11 | Status Accounting Meeting 2 | Project Management |  | 28/08/2022 | Completed | Review tracker, manual test cases and selenium code | 29/08/2022
12 | REST API Testing Distribution | Project Management |  | 2022-01-10 | Completed | Distributed the REST API Testing modules | 2022-03-10
13 | Rest Api Implementation in Postman | Rest_API_Postman |  | 2022-01-10 | Completed | Writing Manual Test cases and automating using postman | 2022-03-10

## Project_Management
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Selecting AUT
1 | Selected AUT | All | 2022-11-07 | Completed | Difficulty Finding project satisfying all the criterias | Exhaustive Searching | 2022-12-07
Problem Statement
1 | Problem Statement 1.0 Creation | ALL | 2022-12-07 | Completed | Unavailablity of Template | Created our own template | 13/07/2022
API Feasibility Check
1 | Git Implementation | ALL | 28/09/2022 | Completed |  | Creating repositories and setting it up on PSL Machines | 2022-02-10
SYNC UP Meetings
1 | Meeting for manual testcases query | ALL | 13/07/2022 | Completed |  |  | 13/07/2022
2 | Meeting for manual testcases finalization | ALL | 30/07/2022 | Completed |  |  | 30/07/2022
Project Related Activites
1 | Created index page and added hyperlinks for manual testcases | Sakshi Majalekar | 14/07/2022 | Completed |  |  | 15/07/2022
|  | Ranjana Shenoy | 14/07/2022 | Completed |  |  | 15/07/2022
Scrum Meetings
1 | Application & Problem statement | Rutuja Jadhav | 25/08/2022 | Completed |  |  | 26/08/2022
2 | Application selection | Sarika Bote | 26/08/2022 | Completed |  |  | 27/08/2022
3 | Setup On PSL | Vishal Mali | 27/08/2022 | Completed |  |  | 28/08/2022
4 | Problem statement 2.0 | Abhijit Kore | 28/08/2022 | Completed |  |  | 29/08/2022
Manual Testing
1 | Test Case | ALL | 20/07/2022 | Completed |  |  | 21/07/2022
2 | Test Scenario | ALL | 20/07/2022 | Completed |  |  | 21/07/2022
3 | ECP-BVA report | Sakshi Majalekar | 15/07/2022 | Completed |  |  | 16/07/2022
4 | Defect report | Sarika Bote | 27/07/2022 | Completed |  |  | 28/07/2022
5 | Execution log report | Rutuja Jadhav | 29/07/2022 | Completed |  |  | 30/07/2022
6 | functional requirements | Abhijit Kore | 14/07/2022 | Completed |  |  | 14/07/2022
7 | Non-functional requirements | vishal Mali | 14/07/2022 | Completed |  |  | 14/07/2022
Rest_API_Postman
1 | Find the API for myntra | Ranjana Shenoy | 2022-01-10 | Completed | Finding the fake API for Myntra | Used the API for other ecommerce websites. | 2022-03-10
2 | Testing using methods like POST, GET. | Ranjana Shenoy | 2022-01-10 | Completed | Status code for POST is 200 Ok instead of 201 | Use of fake API lead to the issue. Actual Data insertion wont take place. Hence 200 OK wont be an error. | 2022-03-10
Selenium
1 | Script writing for search bar and my profile module | Ranjana Shenoy | 25/08/2022 | Completed | Cannot automate save details after editing the details(due to OTP request) | Didn't automated the part | 2022-05-09
2 | Script writing for Place order and My orders module and code integration | Sakshi Majalekar | 25/08/2022 | Completed | Payment part is not accessible | Didn't automated the part | 2022-05-09
3 | Script writing for Help center module and code integration | Sarika Bote | 25/08/2022 | Completed |  |  | 2022-05-09
4 | Script writing for Add to cart and Filter module | Rutuja Jadhav | 25/08/2022 | Completed |  |  | 2022-05-09
5 | Script writing for Login and register module | Vishal Mali | 25/08/2022 | Completed | unnecessary delay and alerts during automation login | Added delay in script and manually handled alerts | 2022-05-09
6 | Script writing for Wishlist module | Abhijit Kore | 25/08/2022 | Completed |  |  | 2022-05-09

## GIT
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Git Implementation
1 | Created local repository | Ranjana Shenoy | 2022-01-10 | Completed | NA | NA | 2022-01-10
2 | Files uploaded to repository | Sakshi Majalekar | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Ranjana Shenoy | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Rutuja Jadhav | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Sarika Bote | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Abhijit Kore | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Vishal Mali | 28/09/2022 | Completed | NA | NA | 2022-02-10

## Manual_Testing
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Manual Test Case Writing
1 | Creating Test Cases and test Scenario for "Login page" | vishal Mali | 20/07/2022 | Completed | NA | NA | 21/07/2022
2 | Creating Test Cases and test Scenario for "Search bar" | Ranjana Shenoy | 20/07/2022 | Completed | NA | NA | 21/07/2022
3 | Creating Test Cases and test Scenario for "My Order" | Sakshi Majalekar | 20/07/2022 | Completed | NA | NA | 21/07/2022
4 | Creating Test Cases and test Scenario for "Filter" | Rutuja Jadhav | 20/07/2022 | Completed | NA | NA | 21/07/2022
5 | Creating Test Cases and test Scenario for "My profile" | Ranjana Shenoy | 20/07/2022 | Completed | NA | NA | 21/07/2022
6 | Creating Test Cases and test Scenario for "Wishlist" | Abhijit Kore | 20/07/2022 | Completed | NA | NA | 21/07/2022
7 | Creating Test Cases and test Scenario for "Register" | vishal Mali | 20/07/2022 | Completed | NA | NA | 21/07/2022
8 | Creating Test Cases and test Scenario for "Add to cart" | Rutuja Jadhav | 20/07/2022 | Completed | NA | NA | 21/07/2022
9 | Creating Test Cases and test Scenario for "Place order" | Sakshi Majalekar | 20/07/2022 | Completed | NA | NA | 21/07/2022
10 | Creating Test Cases and test Scenario for "Help center" | Sarika Bote | 20/07/2022 | Completed | NA | NA | 21/07/2022
11 | Creating ECP-BVA report | Sakshi Majalekar | 15/07/2022 | Completed | NA | NA | 16/07/2022
12 | Creating Execution log report | Sarika Bote | 27/07/2022 | Completed | NA | NA | 28/07/2022
13 | Creating Defect report | Rutuja Jadhav | 29/07/2022 | Completed | NA | NA | 30/07/2022
14 | Creating Functional requirements | Abhijit Kore | 14/7/2022 | Completed | NA | NA | 14/7/2022
15 | Creating Non-Functional requirements | vishal Mali | 14/7/2022 | Completed | NA | NA | 14/7/2022

## Selenium
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Automating Test Cases
1 | Script writing for search bar and my profile module | RANJANA SHENOY K | 25/08/2022 | completed |  |  | 2022-05-09
2 | Script writing for Place order and My orders module and code integration | SAKSHI MAJALEKAR | 25/08/2022 | completed |  |  | 2022-05-09
3 | Script writing for Help center module and code integration | SARIKA BOTE | 25/08/2022 | completed |  |  | 2022-05-09
4 | Script writing for Add to cart and Filter module | RUTUJA JADHAV | 25/08/2022 | completed |  |  | 2022-05-09
5 | Script writing for Login and register module | VISHAL MALI | 25/08/2022 | completed |  |  | 2022-05-09
6 | Script writing for Wishlist module | ABHIJIT KORE | 25/08/2022 | completed |  |  | 2022-05-09

## Rest_API_Postman
SR NO. | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Rest API Implementation in Postman
1 | Find the API for myntra | RANJANA SHENOY K | 2022-01-10 | completed | Finding the fake API for Myntra | Used the API for other ecommerce websites. | 2022-03-10
2 | Testing using methods like POST, GET. | RANJANA SHENOY K | 2022-01-10 | Completed | Status code for POST is 200 Ok instead of 201 | Use of fake API lead to the issue. Actual Data insertion wont take place. Hence 200 OK wont be an error. | 2022-02-10
3 | Data Driven Testing | SARIKA BOTE | 2022-01-10 | completed | Data Driven Testig | Used the API for other ecommerce websites. | 2022-03-10
4 | Login and Register Test | SARIKA BOTE | 2022-01-10 | completed | Token Check | used the fake API for Login Test